**Fresno State**

**WASC Timeline**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **2012 – 2013 AY** |  | **2013 – 2014 AY** |  | **2014 – 2015 AY** |
| **Summer 2012**   * Develop WASC Communication plan |  | **Summer 2013**   * Continue compilation and analysis of data and learning outcomes * WASC Workshop (Offsite review details) |  | **Summer 2014**  **Tentative**  **\*\*Submit WASC Institutional Narrative (CPR) *(3 months before offsite review and no more than 75 pgs.)*** |
| **Fall 2012**   * Implement faculty and campus WASC engagement plan * Check for template availability in November   **Conferences**   * AA AVP’s Meeting – 10/24/12, Long Beach, CA * WASC Meeting – 9/24/12, Irvine, CA |  | **Fall 2013**   * Begin drafting WASC Institutional Narrative |  | **Fall 2014**  **\*\*Offsite Review**   * WASC Skype video conference with visiting team (2-3 hours long) |
| **Spring 2013**  \*\***Submit Preparatory Data**   * Submit financial data * Submit retention/graduation rate data (only undergraduate data for now) |  | **Spring 2014**   * Continue compilation and analysis of data and learning outcomes – collect 2 external benchmarked data |  | **Spring 2015/ Fall 2015**  **\*\*Onsite Review**   * Host Fresno State Student Success and Learning Expo (1-3 day visit) |

|  |
| --- |
| **2012 – 2013 AY** |
| **Summer 2012**   * Develop WASC Communication plan |
| **Fall 2012**   * Implement faculty and campus WASC engagement plan * Check for template availability in November |
| **Spring 2013**  \*\***Submit Preparatory Data**   * Submit financial data * Submit retention/graduation rate data (only undergraduate data for now) |

|  |
| --- |
| **2013 – 2014 AY** |
| **Summer 2013**   * Continue compilation and analysis of data and learning outcomes * WASC workshop (offsite review details) |
| **Fall 2013**   * Begin drafting WASC Institutional Narrative |
| **Spring 2014**   * Continue compilation and analysis of data and learning outcomes – collect 2 external benchmarked data |

|  |
| --- |
| **2014 – 2015 AY** |
| **Summer 2014**  **\*\*Tentative\*\* Submit WASC Institutional Narrative (CPR) *(3 months before offsite review and no more than 75 pgs.)*** |
| **Fall 2014**  \*\***Offsite review**   * WASC Skype video conference with visiting team (2-3 hours long) |
| **Spring 2015/ Fall 2015**  \*\***Onsite Review 1-3 day visit**   * Host Fresno State Student Success and Learning Expo (1-3 day visit) |